## Mikrokosmos
MIKROKOSMOS TEAM
No. | ID - Label | Fullname | Role
1 | mikrokosmos | Mikrokosmos Team | Team
2 | trungdq | Doan Quoc Trung | Leader
3 | ynm | Nguyen Minh Y | Member
4 | tonghh | Ho Hoang Tong | Member
5 | hangptt | Pham Thi Thanh Hang | Member
PROJECT ITEMS
No. | ID | Item name | Tools
1 | AD | Analysis and design project | Enterprise Architect Microsoft Visio Microsoft Word
2 | BD | Build database | MySQL Workbench
3 | WS | Web Service | Eclipse
4 | WM | Web-app Management
5 | OS | Web online store
6 | DA | Desktop application
7 | MA | Mobile application | Visual Studio
8 | T | Test | Eclipse
9 | RP | Report project | Microsoft Excel Microsoft Word Microsoft Powerpoint

## 1st phase
ANALYSIS AND DESIGN PROJECT
ID | Tittle | Detail | Implemented by | Date start | Expected time | Actual time | State
DATABASE
AD01 | Sketch database | Sketch database | mikrokosmos | 2020-09-14 | 12 | 8 | Closed
AD02 | Entity-Relationship Model (hard ver) | Draw ER Model on A3 paper (1-1, 1-n, n-n) | hangptt | 2020-09-17 | 4 | 4 | Closed
AD03 | Entity-Relationship Model (soft ver) | Draw ER Model in Microsoft Word (1-1, 1-n, n-n) | hangptt | 2020-09-18 | 4 | 4 | Closed
AD04 | Entity-Relationship diagram (hard ver) | Draw ERD on A3 paper | ynm | 2020-09-17 | 4 | 4 | Closed
AD05 | Entity-Relationship diagram (soft ver) | Draw ERD in Microsoft Visio | ynm | 2020-09-18 | 4 | 2 | Closed
AD06 | Relational database schema (hard ver) | Draw relational database schema on A4 paper | hangptt | 2020-09-21 | 4 | 4 | Closed
AD07 | Relational database schema (soft ver) | Draw relational database schema in Microsoft Word | hangptt | 2020-09-22 | 4 | 4 | Closed
AD08 | Use case diagram | Draw use case diagram in Enterprise Architect - Login, restore | trungdq | 2020-09-17 | 3 | 2 | Closed
|  | Draw use case diagram in Enterprise Architect - Insert, update, find | ynm | 2020-09-21 | 12 | 10 | Closed
|  | Draw use case diagram in Enterprise Architect - Delete physic, delete logic | hangptt | 2020-09-23 | 10 | 10 | Closed
AD09 | Database structure | Design database structure (column name, data type, size, default, extra, description) | tonghh | 2020-09-17 | 4 | 3 | Closed
PRODUCTS FUNCTION
AD10 | Consequence | Consequence of login function Consequence of register function Consequence of search function Consequence of restore function (in Enterprise Architect) | ynm | 2020-09-24 | 6 | 6 | Closed
|  | Consequence of insert function Consequence of update function Consequence of delete physical function Consequence of delete logic function (in Enterprise Architect) | tonghh | 2020-09-18 | 4 | 4 | Closed
AD11 | Backlog rule | Design backlog rule | trungdq | 2020-09-16 | 8 | 8 | Closed
AD12 | Product backlog | Design product backlog | trungdq | 2020-09-17 | 16 | 16 | Closed
AD13 | Release backlog | Design release backlog | tonghh | 2020-09-21 | 8 | 8 | Closed
AD14 | Sprint backlog | Design sprint backlog | tonghh | 2020-09-23 | 8 | 8 | Closed
REPORT
RP01 | Design Report project template | Design Report project template in Microsoft Word | tonghh | 2020-09-25 | 2 | 1 | Closed
RP02 | Report AD03 |  | hangptt | 2020-09-25 | 1 | 1 | Closed
RP03 | Report AD05 |  | ynm | 2020-09-25 | 1 | 1 | Closed
RP04 | Report AD07 |  | hangptt | 2020-09-25 | 1 | 1 | Closed
RP05 | Report AD08 |  | trungdq | 2020-09-25 | 1 | 1 | Closed
RP06 | Report AD09 |  | tonghh | 2020-09-25 | 1 | 1 | Closed
RP07 | Report AD10 |  | ynm | 2020-09-25 | 1 | 1 | Closed
|  |  | tonghh | 2020-09-25 | 1 | 1 | Closed
|  |  | Start: | 2020-09-14
|  |  | Finish: | 2020-09-25
No. | ID - Label | Standard time | Expected time | Plan time | Actual time
1 | mikrokosmos | 160 | 12 | 12 | 8
2 | trungdq | 40 | 28 | 28 | 27
3 | ynm | 40 | 28 | 28 | 24
4 | tonghh | 40 | 28 | 28 | 26
5 | hangptt | 40 | 28 | 28 | 28
No. | State
1 | NEW
2 | ACTIVE
3 | CLOSED
Formulas:
Date start = MIN(E4:E14,E16:E21,E23:[Date start, row above])

## 2nd phase
BULD DATABASE
ID | Tittle | Detail | Implemented by | Date start | Expected time | Actual time | State
IMPLEMENT
BD01 | Create database | Create database and 17 tables (Primary key, Foreign key, Cascade delete) | trungdq | 2020-09-28 | 6 | 6 | Closed
BD02 | Insert database | > 50 rows: Staffs, Customers. | tonghh | 2020-09-28 | 6 | 6 | Closed
|  | < 05 rows: Catergories, Levels, Method, Depart. < 50 rows: Suppliers, HistoryPrices, Staffs. > 50 rows: others. | hangptt | 2020-09-28 | 18 | 18 | Closed
BD03 | Create Trigger | Create constraint trigger Create log trigger | tonghh | 2020-10-01 | 12 | 12 | Closed
BD04 | Create Stored procedure | 1. Create SP to insert (insert into) 2. Create SP to update (update) | trungdq | 2020-10-02 | 12 | 12 | Closed
|  | 3. Create SP to delete physical (delete) 4. Create SP to delete logic (update_isDel=0) 5. Create SP to read with isDel=0 (select_where) 6. Create SP to read data with isDel=1 (select_where) 7. Create SP to find (select_where) 8. Create SP to restore (update_isDel=1) | ynm | 2020-09-28 | 18 | 18 | Closed
REPORT
RP01 | Design Report code template | Design Report code template in Microsoft Excel | tonghh | 2020-10-02 | 1 | 1 | Closed
RP02 | Report BD01 | Report code create database | trungdq | 2020-10-02 | 1 | 1 | Closed
RP03 | Report BD02 | Report quantity of data inserted for each table | hangptt | 2020-10-02 | 2 | 2 | Closed
RP04 | Report BD03 | Report code create constraint trigger Report code create log trigger | tonghh | 2020-10-02 | 1 | 1 | Closed
RP05 | Report DB04 | Report code create SP to insert, update | trungdq | 2020-10-02 | 1 | 1 | Closed
|  | Report code create SP to delete physical, delete logic, find, restore, read with isDel=0 and isDel=1 | ynm | 2020-10-02 | 2 | 2 | Closed
|  |  | Start: | 2020-09-28
|  |  | Finish: | 2020-10-02
No. | ID - Label | Standard time | Expected time | Plan time | Actual time
1 | mikrokosmos | 80 | 0 | 0 | 0
2 | trungdq | 20 | 20 | 20 | 20
3 | ynm | 20 | 20 | 20 | 20
4 | tonghh | 20 | 20 | 20 | 20
5 | hangptt | 20 | 20 | 20 | 20
No. | State
1 | NEW
2 | ACTIVE
3 | CLOSED
Formulas:
Date start = MIN(E4:E9,E11:[Date start, row above])

## 3rd phase
WEB SERVICE
ID | Tittle | Detail | Implemented by | Date start | Expected time | Actual time | State
IMPLEMENT
WS01 | Create project frame | Create project frame in the Eclipse (Maven project) | trungdq | 2020-10-05 | 8 | 8 | Closed
WS02 | Create model | Mapping data to model | ynm | 2020-10-05 | 12 | 12 | Closed
WS03 | Valid data type | Constraint datatype in model | ynm
WS04 | Function login | Handle fucntion login and confirm role of the account owner | ynm | 2020-10-05 | 12 | 12 | Closed
WS05 | Function read with user role | Handle fucntion read data with isDel=0 | hangptt | 2020-10-06 | 4 | 4 | Closed
WS06 | Function read with admin role | Handle fucntion read data with isDel=1 | hangptt | 2020-10-07 | 4 | 4 | Closed
WS07 | Function insert | Handle fucntion insert new data | ynm | 2020-10-08 | 4 | 4 | Closed
WS08 | Function update | Handle fucntion update data | ynm | 2020-10-09 | 4 | 4 | Closed
WS09 | Function delete physical | Handle fucntion delete physical | ynm | 2020-10-10 | 4 | 4 | Closed
WS10 | Function delete logic | Handle fucntion delete logic | ynm | 2020-10-11 | 4 | 4 | Closed
WS11 | Function search | Handle fucntion search | hangptt | 2020-10-12 | 4 | 4 | Closed
WS12 | Function restore | Handle fucntion restore | ynm | 2020-10-13 | 4 | 4 | Closed
WS13 | Function send mail automatic | Handle fucntion send mail automatic | trungdq | 2020-10-14 | 10 | 10 | Closed
TEST
T01 | Design test plan |  | tonghh | 2020-10-14 | 4 | 4 | Active
T02 | Design test design |  | tonghh | 2020-10-15 | 4 | 4 | Active
T03 | Design test case |  | tonghh | 2020-10-16 | 8 | 8 | Active
T04 | Test unit | Test WS04 to WS13 | hangptt | 2020-10-16 | 20 | 20 | Active
REPORT
RP01 | Design Report code template | Design WS Report code template in Microsoft Excel | tonghh | 2020-10-05 | 4 | 4 | Active
RP02 | Report WS01 | Report project frame | trungdq | 2020-10-05 | 2 | 2 | Active
RP03 | Report WS02 | Report model | ynm | 2020-10-05 | 2 | 2 | Active
RP04 | Report WS03 | Report code constrain datatype | ynm |  |  |  | Active
RP05 | Report WS04 | Report code function login | ynm | 2020-10-05 | 2 | 2 | Active
RP06 | Report WS05 | Report code function read with user role | hangptt | 2020-10-06 | 2 | 2 | Active
RP07 | Report WS06 | Report code function read with admin role | hangptt | 2020-10-21 | 2 | 2 | Active
RP08 | Report WS07 | Report code function insert | ynm | 2020-10-22 | 2 | 2 | Active
RP09 | Report WS08 | Report code function update | ynm | 2020-10-23 | 2 | 2 | Active
RP10 | Report WS09 | Report code function delete physical | ynm | 2020-10-10 | 2 | 2 | Active
RP11 | Report WS10 | Report code function delete logic | ynm | 2020-10-16 | 2 | 2 | Active
RP12 | Report WS11 | Report code function search | hangptt | 2020-10-17 | 2 | 2 | Active
RP13 | Report WS12 | Report code function restore | ynm | 2020-10-18 | 2 | 2 | Active
RP14 | Report WS13 | Report code function send mail automatic | ynm | 2020-10-19 | 2 | 2 | Active
RP15 | Design test defect | Design test defect template in excel | hangptt | 2020-10-20 | 2 | 2 | Active
RP16 | Report T04 | Report test unit result | hangptt | 2020-10-21 | 12 | 12 | Active
|  |  | Start: | 2020-10-05
|  |  | Finish: | 2020-10-23
No. | ID - Label | Standard time | Expected time | Plan time | Actual time
1 | mikrokosmos | 240 | 0 | 0 | 0
2 | trungdq | 60 | 60 | 20 | 20
3 | ynm | 60 | 60 | 60 | 60
4 | tonghh | 60 | 60 | 20 | 20
5 | hangptt | 60 | 60 | 52 | 52
No. | State
1 | NEW
2 | ACTIVE
3 | CLOSED
Formulas:
Date start = MIN(E4:E16,E18:E21,E23:[Date start, row above])

## 4th phase
WEB-APP MANAGEMENT
ID | Tittle | Detail | Implemented by | Date start | Expected time | Actual time | State
IMPLEMENT
WM01 | Template | Redesign template | tonghh | 2020-10-26 | 16 | 16 | Active
WM02 | Login | Login and confirm role of the account owner | ynm | 2020-10-26 | 18 | 18 | Active
WM03 | Show data | Show data for each role: -Table | trungdq | 2020-10-26 | 6 | 6 | Active
|  | Show data for each role: -Table | tonghh | 2020-10-30 | 4 | 4 | Active
WM04 | Function insert | Insert new data for tables: - | trungdq | 2020-10-27 | 6 | 6 | Active
|  | Insert new for tables: - | tonghh | 2020-11-02 | 4 | 4 | Active
WM05 | Function update | Update data for tables: - | trungdq | 2020-10-29 | 6 | 6 | Active
|  | Update data for tables: - | tonghh | 2020-11-03 | 4 | 4 | Active
WM06 | Function delete | Delete data for tables: - | trungdq | 2020-10-30 | 6 | 6 | Active
|  | Delete data for tables: - | tonghh | 2020-11-04 | 4 | 4 | Active
WM07 | Function restore | Restore in page Recycle Bin | trungdq | 2020-11-03 | 6 | 6 | Active
WM08 | Function search | Search for tables: - | tonghh | 2020-11-05 | 4 | 4 | Active
|  | Search for tables: - | trungdq | 2020-11-04 | 4 | 4 | Active
WM09 | Business statistics | Show bussiness statistics | trungdq | 2020-11-05 | 12 | 12 | Active
TEST
T01 | Design test plan |  | tonghh | 2020-11-06 | 2 | 2 | Active
T02 | Design test design |  | tonghh | 2020-11-06 | 2 | 2 | Active
T03 | Design test case |  | tonghh | 2020-11-09 | 4 | 4 | Active
T04 | Test automation | Test WM02 to WM08 | hangptt | 2020-10-26 | 20 | 20 | Active
REPORT
RP01 | Design Report code template | Design WM Report code template in Microsoft Excel | tonghh | 2020-11-10 | 4 | 4 | Active
RP02 | Template | Report main components of template | tonghh | 2020-11-11 | 2 | 2 | Active
RP03 | Login | Report code to login and confirm roles | ynm | 2020-10-30 | 2 | 2 | Active
RP04 | Show data | Report code show data | trungdq | 2020-11-10 | 2 | 2 | Active
|  | Report code show data | tonghh | 2020-11-11 | 2 | 2 | Active
RP05 | Function insert | Report code insert data | trungdq | 2020-11-11 | 2 | 2 | Active
|  | Report code insert data | tonghh | 2020-11-12 | 2 | 2 | Active
RP06 | Function update | Report code update data | trungdq | 2020-11-11 | 2 | 2 | Active
|  | Report code update data | tonghh | 2020-11-12 | 2 | 2 | Active
RP07 | Function delete | Report code delete data | trungdq | 2020-11-12 | 2 | 2 | Active
|  | Report code delete data | tonghh | 2020-11-13 | 2 | 2 | Active
RP08 | Function restore | Report code restore data | trungdq | 2020-11-12 | 2 | 2 | Active
RP09 | Function search | Report code search data | tonghh | 2020-11-13 | 2 | 2 | Active
|  | Report code search table | trungdq | 2020-11-13 | 2 | 2 | Active
RP10 | Business statistics | Report code | trungdq | 2020-11-13 | 2 | 2 | Active
RP11 | Design test defect | Design test defect | hangptt | 2020-11-02 | 2 | 2 | Active
RP12 | Report T04 | Report code of test tool and result of test | hangptt | 2020-11-02 | 6 | 6 | Active
|  |  | Start: | 2020-10-26
|  |  | Finish: | 2020-11-13
No. | ID - Label | Standard time | Expected time | Plan time | Actual time
1 | mikrokosmos | 240 | 0 | 0 | 0
2 | trungdq | 60 | 60 | 60 | 60
3 | ynm | 60 | 60 | 20 | 20
4 | tonghh | 60 | 60 | 60 | 60
5 | hangptt | 60 | 60 | 28 | 28
No. | State
1 | NEW
2 | ACTIVE
3 | CLOSED
Formulas:
Date start = MIN(E4:E17,E19:E22,E24:[Date start, row above])

## Final phase
ID | Tittle | Detail | Implemented by | Date start | Expected time | Actual time | State
TEST
2020-11-30
REPORT
2020-12-04
|  |  | Start: | 2020-11-30
|  |  | Finish | 2020-12-04
No. | ID - Label | Standard time | Expected time | Plan time | Actual time
1 | mikrokosmos | 80 | #REF! | #REF! | #REF!
2 | trungdq | 20 | #REF! | #REF! | #REF!
3 | ynm | 20 | #REF! | #REF! | #REF!
4 | tonghh | 20 | #REF! | #REF! | #REF!
5 | hangptt | 20 | #REF! | #REF! | #REF!
No. | State
1 | NEW
2 | ACTIVE
3 | CLOSED
Formulas:
Date start = MIN(E3:E7,E9:[Date start, row above])